Executive summary

This work describes the plan for the development of a Car Simulator for use in driving schools. Sponsored by Sebastien Donais for the MECH8106 25F Capstone Project at Conestoga College, this project involves creating a cost-effective, functional, and manufacturable simulator of uphill and downhill driving.

The end goal is to generate a complete SolidWorks design of the simulator, including all structural components, mounting for gaming controls, panel for a 32” curved monitor, PC integration, and pneumatic system for the dynamic motion. Simultaneously, the team will create a manufacturing implementation plan that will secure process flow, plant layout, material and inventory management, equipment selection, tooling, staffing, Quality Assurance, and budgeting. The production line will be configured to produce about 10,000 units annually.

The project deliverables include:

- 3D models and assemblies (Week 7).

- Detail 2D drawings for production (Week 14).

- manufacturing deployment plan with resource, cost, and quality tolerances (Week 14).

- A final report containing the complete project documentation, results, experience, and recommendations (Week 15).

The project will be executed using a hybrid agile methodology, organised into six two-week sprints in order to facilitate iterative development, ongoing feedback, and sponsorship alignment. Sponsors meet weekly and have scheduled progress submissions to provide continued points of evaluation.

Highlights of the plan:

- SolidWorks in combination with MS Teams and OneDrive for collaborative design and documentation.

- Incorporation of pneumatic systems to replicate realistic driving environments.

- A scalable and cost-effective plan of production, including cost estimates for materials, tools, equipment, labor, and quality control.

- Well-aligned with customer requirements and industry accepted at both technical and commercial levels.

Scope of Work

This project scope includes the entire process of designing, documenting, and planning to manufacture an economical Car Simulator that can be used in driving schools. The simulator will be designed to specifically simulate the experience of uphill and downhill driving, and it will be designed to be durable, affordable, and easily manufacturable.

The work will be separated into two primary streams: design and engineering on the one hand, and manufacturing planning and implementation on the other hand.

- Design

- Creation of a full SolidWorks model of the simulator, structural frame, support system, gaming control mounting brackets, and a 32-inch curved monitor case.

- Design of the PC enclosure into the simulator to provide smooth integration of the software and hardware.

- Design of pneumatic systems that would act like realistic driving dynamics, such as incline, decline, and motion response.

- Creation of 3D assemblies (by Week 7) and elaborate 2D engineering illustrations to fabricate (by Week 14).

- Planning and Deployment in Manufacturing.

- Draw-up of a manufacturing plan including process flow, plant layout, equipment selection, tooling, and staffing requirements.

- Determination of material needs, inventory management procedures, and estimations of costs of all the significant inputs.

- Production plan development that could sustain an output of about 10,000 units in annual production.

- Installation of quality assurance guidelines and associated tolerances on material, cost, and process control.

- Provocation of a consolidated deployment plan (by Week 14) and a final full report (by Week 15).

- Collaboration and Project Management.

- The project implementation was carried out with the hybrid agile approach that consisted of six two-week sprints that enabled constant feedback and reiteration.

- Sponsor meetings and planned submission of progress each week to ensure alignment with the project goals.

- Team communication and collaborative documentation: Teams and OneDrive are used.

The scope is purely the design, planning, and documentation of the simulator and the process of producing the simulator itself. The unit is not yet within the scope of actual prototyping, testing or large-scale manufacturing, although the outputs of this project will inform such.

project timeframes, scheduling and milestones

Car Simulator Project Budget and Resources

1. Material and Inventory Budget (Bill of Materials - BOM)

Inventory Strategy: It will be a Hybrid Kanban / Just-in-Time (JIT) system. Purchasing parts (high value items like pneumatics, purchased parts) will be stocked JIT and a 3-day safety stock. The bulk raw materials (steel) will be ordered once a month.

| Category | Item Description | Cost per Unit (CAD) | Annual Qty | Total Annual Cost (CAD) | Sourcing Strategy |
| --- | --- | --- | --- | --- | --- |
| Structural | 16GA & 14GA CR Steel Sheet | $25.00 | 10,000 | $250,000 | Bulk order from steel mill. |
|  | 2"x2" & 1"x1" SQ Tube 11GA | $55.00 | 10,000 | $550,000 | Bulk order from steel mill. |
| Pneumatics | Dual-Acting Pneumatic Cylinders (2x) | $110.00 | 20,000 | $2,200,000 | Contract with manufacturer (SMC/Festo). |
|  | Solenoid Valves, FRL, Tubing | $50.00 | 10,000 | $500,000 | Kitted from supplier. |
| Purchased Parts | Gaming Seat | $85.00 | 10,000 | $850,000 | Sourced from automotive supplier. |
|  | Force Feedback Wheel & Pedals | $160.00 | 10,000 | $1,600,000 | OEM Partnership (Logitech). |
|  | 32" Curved Monitor Mount | $20.00 | 10,000 | $200,000 | Custom fabricated bracket. |
| Hardware & Elec. | Fasteners (Bolts, Nuts, Screws) | $12.00 | 10,000 | $120,000 | Kitted from supplier (McMaster-Carr). |
|  | Wiring Loom & Connectors | $8.00 | 10,000 | $80,000 | Assembled in-house. |
| Finishing | Powder Coating (Primer & Coat) | $35.00 | 10,000 | $350,000 | Outsourced to local coater. |
| Total Per Unit Cost |  | $560.00 |  |  |  |
|  | Total Annual Material Cost |  |  | $6,700,000 |  |

2. Equipment and Machinery (Capital Expenditure - CAPEX)

| Equipment | Qty | Unit Cost (CAD) | Total Cost (CAD) | Justification & Utilization |
| --- | --- | --- | --- | --- |
| CNC Fiber Laser Cutter | 1 | $220,000 | $220,000 | High-speed cutting for all sheet metal. 85% utilization. |
| CNC Press Brake | 2 | $110,000 | $220,000 | Bending all brackets and panels. 90% utilization. |
| Robotic Welding Cell | 1 | $350,000 | $350,000 | For consistent, high-quality frame welds. 80% utilization. |
| Manual Welding Stations (MIG) | 3 | $12,000 | $36,000 | For non-standard attachments and rework. |
| Powder Coating Line | 1 | $280,000 | $280,000 | In-house control over quality and timing. |
| Assembly Station Tools | 10 | $3,000 | $30,000 | Electric torque wrenches, drills, etc. |
| Pneumatic Test Rig | 2 | $8,000 | $16,000 | QA testing for every unit. |
| Total Estimated CAPEX |  |  | $1,152,000 |  |

3. Human Resource Plan & Labour Budget

| Role | # of Employees | Hourly Wage (CAD) | Annual Salary (CAD) | Total Annual Cost (CAD) | Key Responsibilities |
| --- | --- | --- | --- | --- | --- |
| Production |  |  |  |  |  |
| Laser/Press Operator | 2 | $29.00 | $60,320 | $120,640 | Operate CNC machines, perform basic maintenance. |
| Welding Technician | 3 | $33.00 | $68,640 | $205,920 | Operate robotic cell and manual stations. |
| Assembly Technician | 6 | $27.00 | $56,160 | $336,960 | Full unit assembly and wiring. |
| Support |  |  |  |  |  |
| Production Supervisor | 1 | $42.00 | $87,360 | $87,360 | Oversee line, solve issues, manage schedule. |
| QA/QC Inspector | 2 | $31.00 | $64,480 | $128,960 | In-process and final inspection. |
| Maintenance Tech | 1 | $38.00 | $79,040 | $79,040 | Maintain all equipment, prevent downtime. |
| Total Annual Gross Salary |  |  |  | $958,880 |  |
| Benefits & Burden (25%) |  |  |  | $239,720 | Includes healthcare, CPP, EI, etc. |
| Total Annual Labour Cost |  |  |  | $1,198,600 |  |

4. Master Budget and Phased Funding Requirements

| Phase | Timeline | Budget Item | Total Cost (CAD) | Details & Justification |
| --- | --- | --- | --- | --- |
| Phase 1: Capital Investment | Month 0-2 | Equipment Purchase (CAPEX) | $1,152,000 | One-time cost. Secured via business loan or investment. |
|  |  | Facility Setup & Installation | $150,000 | Electrical, air lines, safety equipment. |
|  |  | Subtotal Phase 1 | $1,302,000 | Funding required at project start. |
| Phase 2: Production Ramp-Up | Month 3-4 | Initial Inventory & Working Capital | $1,200,000 | Covers first 2 months of raw material purchases and labour before revenue from sales begins. |
| Phase 3: Steady-State Production | Month 5+ | Annual Operational Cost (OPEX) |  |  |
|  |  | Materials & Components | $6,700,000 | Recurring, volume dependent. |
|  |  | Labour & Benefits | $1,198,600 | Fixed annual cost. |
|  |  | Overhead (Rent, Utilities, etc.) | $300,000 | Estimated for a 20,000 sq ft facility. |
|  |  | Total Annual OPEX | $8,198,600 |  |
|  |  | Monthly OPEX | $683,217 |  |